## Bug Report
Bug ID | Module | Title | Severity | Priority | Steps to Reproduce | Expected Result | Actual Result | Affected TC(s) | Status | Notes
BUG-001 | Registration | Missing Confirm Password field on registration form | Medium | Medium | 1. Navigate to /index.php?route=account/register 2. Observe the password section of the form | A Confirm Password field should be present to validate that the user has typed their password correctly. | Only a single Password field exists. No password confirmation is required. | TC-003 | Open | User can mistype their password during registration with no validation, potentially locking themselves out of their account.
BUG-002 | Registration, Login | Error and validation messages display in upper right corner and are easy to miss | Low | Low | 1. Navigate to the registration or login page 2. Trigger any validation or error message (e.g. submit blank fields, enter wrong password) | Error messages should appear inline near the relevant field or in a prominent, noticeable location. | Messages appear in the upper right corner of the page and can be easily overlooked by the user. | TC-004, TC-005, TC-007, TC-008, TC-009, TC-010 | Open | Affects both Registration and Login modules. Poor message placement may cause user confusion.